## Wheel Clamp IoT
# | Task | Details | Completion Date | Comments
1 | Purchase required electronic components | Electronics end state: Arduino is connected with GPS & GSM chip and capable of running a servo / solenoid through a relay | 2019-05-21
2 | Fix all electronics in the required manner | GSM chip connects to Arduino and can receive SMS. Send sms from another phone for the Arduino to lock / ublock the solenoid | 2019-05-25
3 | Embedded C programming | 1. receive SMS and unlock 2. receive SMS with a hardcoded PIN and only then unlock 3. send out GPS coordinates | 2019-06-07
4 | Mechanical aspect |  | 2019-06-09 | Satish to talk to Homeshwar
5 | Solenoid | 1. Electronically make solenoid work 2. Build the solenoid inside the mechanical box 3. Interact with the solenoid through a relay to lock / unlock
6 | Create 3-D print file | Go through the Youtube videos, pick an opensource software to create the 3-D print file | 2019-06-14
7 | Mobile interfacing with this device using a simple app | Dynamic PIN / OTP / QR code based unlock | 2019-06-19 | Identify an Android developer
8 | Mobile app | Payment gateway | 2019-06-19 | Identify an Android developer
9 | Mechanical aspect (3-D printing) | Print the 3-D model in plastic | 2019-06-20
10 | Review of Documentation | Review all tech documentation - electronics, mechanical, code | 2019-06-21
11 |  |  | TBD
12
13
14
15
16
17